Minutes of the First MEDIN Sponsors’ Board

held at the MRC, London on

Monday 22nd September 2008

Present

Peter Liss		Chair

Gareth Boon		MOD

Juan Brown		NERC (BODC)

Darius Campbell	Defra

David Cotton		MEDIN

Mike Cowling		The Crown Estate

Martyn Cox		Scottish Government

Tabitha Dale		Defra

Trevor Guymer	IACMST/MSCC

Chris Luton		NERC (BGS) for item 7

Alison Miles		Environment Agency

Kevin O’Carroll	DBERR

Mike Osborne		SeaZone

David Parker		Countryside Council for Wales

John Pepper		UKHO

Lesley Rickards	MEDIN

Ian Townend		HR Wallingford

Malcolm Vincent	JNCC

By Teleconference

Claire Vincent		DOENI

Apologies

Jon Turton		Met Office

Rob Spillard		MCA

1.	Welcome and Introductions

1.1	Chair welcomed those present to meeting and thanked them for their support 	and financial contributions to MEDIN.  Meeting also reflected on sad loss of 	Professor Sir Howard Dalton, both to MEDIN and to the marine science 	community.

2. 	MEDIN Proposed Activities 2008 - 2013

2.1	David Cotton provided overview of what MEDIN plans to achieve for its 	sponsors and partners by 2011, the end date of current Sponsors’ Agreements, 	and on 	to 2013 (Papers 1 and 1b refer).  Sponsors were invited to review and 	comment upon proposed objectives, key deliverables and seven inter-linked 	work streams based around the key drivers of UKMMAS, Charting Progress 	2, MMOs, the Marine Strategy Directive, and INSPIRE.

2.2	It was queried which organisations will be hosting DACs.  Those currently within the MEDIN DAC network, or in the process of joining the network are as follows:

British Oceanographic Data Centre (BODC)
	British Geological Survey (BGS)
	Data Archive for Seabed Species and Habitats (DASSH)
	UK Hydrographic Office (UKHO).

2.3	In reference to the identification of key drivers and associated dates, it was felt 	that key drivers should reflect those published within the UK Key Location 	Strategy, which is soon to be published.  The UK’s implementation of 	INSPIRE goes much further than what MEDIN is currently planning to do in 	terms of the licensing and the sharing of data and it is imperative that both the 	UK Key Location Strategy and MEDIN are in tune.  Interestingly, no input to 	the UK Key Location Strategy was sought from marine organisations apart 	from MOD, Met Office and UKHO.  It was also felt that ‘Offshore’ needs to 	be perceived as a key driver.

2.4	Sponsors felt that more geology and core catalogues need to be available via 	MEDIN portal, including access to pertinent European catalogues.  The issue 	of catalogues held by MEDIN needs to be addressed by the MEDIN Executive 	Team.

Action: Executive Team

2.5	Some sponsors queried whether the signing and exchange of MEDIN Sponsor Agreements should wait until key deliverable dates are finalised, and, once these dates are finalised, how flexible they will be.  David Cotton proposed to update the work plan (for the current financial year) to provide deliverable dates in the form of year quarters. This approach was broadly accepted.

Action: David Cotton

2.6	There was discussion regarding the web portal and how ambitious and efficient this had proved to be and what plans there were for the future.  The response was that the portal is low risk in IT terms and provides a realistic solution to user needs.  The greatest effort is concentrated on the production and publication of metadata records.

3.	MEDIN Organisational Arrangements

3.1	Reporting Process

3.1.1	It was agreed the MEDIN coordinator will generate an annual report to the 	Sponsors’ Board and to MSCC.

3.1.2	It was further agreed that the MEDIN Work Stream leaders will provide 	annual 	work plans for approval by the Sponsors’ Board as well as generating 	quarterly reports to meetings of the MEDIN Executive Team.

3.1.3	MEDIN Partners’ will report annually on their progress in meeting their commitments within MEDIN and a summary of these reports will be published on the MEDIN website with the caveat that anything published  	will not breach individual Partners’ ‘commercial in confidence’ regulations. The aim is to assess progress towards meeting the partner requirements, and identify what further work needs to be done, not to publicly embarrass partners.

3.1.4	The Executive Team/Sponsors’ Board to further discuss the publication of an annual report, summarising MEDIN activities, and which will be available in the public domain.

Action: Sponsors’ Board/Executive Team

3.2	Organisational Arrangements

3.2.1	The following was agreed:

- The governing body of MEDIN will be the Sponsors’ Board

- Membership will consist of one representative per sponsoring body

- The Sponsors’ Board will next meet in April 2009, at which meeting a decision will be taken whether to meet annually or biannually

- Sponsors’ Board meetings to be called by MSCC and arranged by the MEDIN core team

- The Chair of the Sponsors’ Board to be appointed by MSCC

- David Cotton to report at each Sponsors’ Board meeting and also produce quarterly reports, highlighting any key milestones achieved.

3.2.2	An annual open Partners’ forum will meet at least once a year. It is planned to hold the next meeting in Q4 2008. The remit of the Partners’ Forum in terms of directing MEDIN work was queried. Lesley Rickards advised that MEDIN would of course accept guidance and recommendations from the Partners’ Forum, but that the Sponsors’ Board was the body responsible for approving the work plan.

3.2.3	DAC Expert Group to meet at least once a year and to hold at least one 	workshop per year, supported by MEDIN Core Team member.

3.3	Executive Team

3.3.1	The MEDIN Executive Team will meet quarterly. Sponsors’ membership was 	agreed as follows:

Martyn Cox		Scottish Government

Darius Campbell 	Defra

Juan Brown		BODC

John Pepper		UKHO.

It was further agreed that Professor Peter Liss will act as Chair, and that the 	remaining membership will comprise of the MEDIN ‘Core’ team (David 	Cotton, Lesley Rickards, Mark Charlesworth and Gaynor Evans) and three 	‘expert’ members to be proposed.

3.4	Publicity

3.4.1	It was felt that much more could be done to promote MEDIN.   Sponsors are asked to carry MEDIN literature at any event they may be attending, and some kind of information sharing network needs to be established so that Sponsors and Partners are aware of new initiatives and can disseminate information (including articles published) accordingly. It was proposed that a communications plan be prepared.

Action: Sponsors’ Board and MEDIN Core Team

3.4.2	A new MEDIN leaflet is planned, which will be distributed to Sponsors on 	publication.

Action: David Cotton

3.4.3	A MEDIN launch event was also discussed but the feeling of the meeting was not in favour.

4. 	Financial Overview

4.1	David Cotton provided an overview of MEDIN finances.  Allocation of funding must be cautious until the amount available is finalised.

4.2	Agreement over spread of funds over different work streams.

4.3	MEDIN has allocated a budget to provide support to DACs in terms of extra resources required to meet requirements of MEDIN DAC network (up to 10K per DAC). Each DAC will be required to make a case for funding and any funding will need to be matched by the DAC either in finance or in kind).  Approval for MEDIN funding will be the responsibility of the Executive Team.

4.4	There is a requirement for an additional Core team member to provide IT 	support (funded preferably via MEDIN budget). If any of the Sponsor 	organisations can suggest someone to fill this role, please advise David 	Cotton.

Action: Sponsors’ Board

4.5	Some Sponsors asked about the basis of the calculation of the Full Economic 	Cost for employing staff through NERC. David Cotton advised that NERC 	FEC rates were calculated according to Treasury Guidelines.

5.	Sponsor and Partner Commitments

5.1	Lesley Rickards advised meeting of the extent of commitments required from 	Sponsors and Partners (all Sponsors are also Partners) to meet MEDIN 	objectives.

5.2	Some Sponsors advised that they would be unable to sign up to the full range of metadata and data sharing aspects of the MEDIN Sponsor/Partner agreement because of potential ‘commercial in confidence’ and national security issues. It was agreed this matter to be discussed outside of the meeting with individual Sponsors approaching David Cotton who will then review the need for individual arrangements.

Action: all Sponsors and Partners

5.3	It was felt important that all Sponsors and Partners strive for a clear and 	common set of pricing and licensing policies.

5.4	Data Clause for Tender Specification

5.4.1	MEDIN has been attempting to develop a generic clause that can be 	included in tender specifications and which will form a fundamental part of 	any contract from the very start of the data collection process and ideally 	before data is collected to ensure data collection is done to an agreed standard.

5.4.2	The clauses were agreed but should be applied to Marine Environmental 	Data. Currently the clause document is entitled Marine Data – which could be 	taken to refer to a wider range of data than intended (e.g. shipping).

5.4.3	Further feedback on the clause gratefully received by David Cotton.

6.	Arrangements post IACMST

6.1	Trevor Guymer reported on progress of the Marine Science Coordination Committee, the successor to IACMST.  MSCC held its first full meeting in July 2008 where it was agreed that ownership of MEDIN will be transferred unchanged to MSCC who should be sent a synopsis of MEDIN proposals and work plans. The date of the next full MSCC meeting is not yet known but it is hoped to be before January 2009. It was agreed that David Cotton should prepare a synopsis of the MEDIN proposals etc. and send this to MSCC (John Lock, Defra and Martyn Cox, Scottish Government) by November 2008.

Action: David Cotton

6.2	The Secretariat of MSCC has yet to be recruited so for the interim, the existing 	IACMST Secretariat will continue in post, funded by NERC (who will also 	part-fund the existing Secretariat on its transfer to MSCC).

6.3	The existing Secretariat is currently gathering information for the UK Strategy for Marine Science (this has not yet formally been asked for by MSCC but there is, however, a need for this information to be compiled no later than mid 2009).

7.	‘High-Level’ Data Strategy/Policy Discussion

7.1	John Pepper asked for the meeting’s views on the requirement for a Marine 	Data Policy Committee (MDPC) within MEDIN that would consider high 	level marine data policy and strategy. Currently, there is little cohesion in 	regard to marine data, with providers each having their own terms and 	conditions resulting in a fragmented and confusing service to both end user 	and provider.

7.2	It is anticipated that a Marine Data Policy Committee would strive to:

- Establish across the marine community an understanding of IP and provide guidance on data exchange, commercialisation and rights management

- Promote a coordinated approach to data capture

- Provide policy and strategy direction

- Facilitate delivery of authoritative datasets

- Demonstrate best practice and ensure marine data strategies (within the forthcoming UK Marine Strategy) are authoritative and comprehensive.

7.3	Whilst there was agreement that a more cohesive stance is required, it was felt 	this issue should be addressed as follows:

- A working group to be formed to identify and prepare a paper on data issues not addressed by MEDIN

- The working group to consist of John Pepper as Chair plus any other Sponsors who feel they can contribute to the working group (please contact john.pepper@ukho.gov.uk if you are interested)

- Paper to be presented to MEDIN Sponsors in first instance for comment and then to MSCC.

Action: Sponsors

8.	Any Other Business and Date of Next meeting/s

8.1	The next Sponsors’ Board meeting will take place in April 2009.

  - The next Partners’ meeting will take place in Q4 2008.

Action List

|  | Action | Status |
| --- | --- | --- |
| 1 | Executive Team: More geology and core catalogues to be available via the portal | To be considered in the specifications for the new portal |
| 2 | David Cotton: To update the list of deliverables for 2008-09 to include dates | Completed and circulated Q4 2008 |
| 3 | Executive Team: Consider publication of the Annual Report as a public document | Executive Team decided a “Glossy Report” was not appropriate at this stage. It is planned to make the current form of the Annual Report available on the MEDIN website. |
| 4 | MEDIN Communications Team: Generate a communications Plan | Completed and discussed by Executive Team, 27/02/09. |
| 5 | MEDIN Communications Team: Distribute leaflet to sponsors | Leaflet and other PR material generated, to be distributed Q2 2009 |
| 6 | Sponsors’ Board: Advise MEDIN core team of any staff available for secondment to provide IT support | No response |
| 7 | Sponsors and Partners: Review Partnership Agreement and need for modification | Agenda issue for this meeting |
| 8 | David Cotton: Prepare MEDIN synopsis for MSCC | Completed Q4 2008. THG to update on MSCC? |
| 9 | Sponsors: Establish Working Group to review need to derive recommendations on data policy | Working Group set up: Agenda issue for this meeting. |